## TASKS
Priority key: |  |  | Completion:
High: Critical need requiring immidiate action, work cannot continue | Medium: Normal priority, not an immediate blocker on the project | Low: Low impact requiring no immediate action | Mark between 0-100, when emails sent to lecturers mark as 50
Issue Log
Issues/ Queries | Comment | Date Raised | Priority | % COMPLETE | Resolved | Response
Query | Are we limited to waterproof/ overwater technology | 2016-10-10 | Medium | 100% | 100% | Not limted per se
Query | What is debris made of? i.e. what sensor might we need? | 2016-10-10 | Medium | 100% | 100% | LDRs and acoustic sensors on order
Query | Does the chassis need waterproofing? | 2016-10-10 | Medium | 100% | 1 | No
Query | Is the drop zone where the robots will be placed | 2016-10-10 | Medium | 100% | 1 | Yes
Query | Will we lose marks for non-waterproof tech? | 2016-10-10 | Medium | 100% | 1 | Not explicitly, need to justify