## TASKS
Priority key: |  |  | Completion:
High: Critical need requiring immidiate action, work cannot continue | Medium: Normal priority, not an immediate blocker on the project | Low: Low impact requiring no immediate action | Mark between 0-100, when emails sent to lecturers mark as 50
Issue Log
Issues/ Queries | Comment | Date Raised | Priority | % COMPLETE | Resolved | Response
Query | Are we limited to waterproof/ overwater technology | 2016-10-10 | Medium | 100% | 100% | Not limted per se
Query | What is debris made of? i.e. what sensor might we need? | 2016-10-10 | Medium | 100% | 100% | LDRs and acoustic sensors on order
Query | Does the chassis need waterproofing? | 2016-10-10 | Medium | 100% | 1 | No
Query | Is the drop zone where the robots will be placed | 2016-10-10 | Medium | 100% | 1 | Yes
Query | Will we lose marks for non-waterproof tech? | 2016-10-10 | Medium | 100% | 1 | Not explicitly, need to justify
Issue | Raspberry Pi network cannot access EDUROM | 2016-11-14 | High | 0% | 0 | Luke has been trying to get on to Edurom therefore worked from home - spoken to Alex couldn't fix; Pi would still not access Edurom
Issue | Kinect cables have not yet arrived | 2017-01-10 | High | 100% | 1 | Arrived 20th
Issue | Set Up Wifi corrupted Raspberry Pi | 2017-01-14 | High | 100% | 1 | Ben had to reformat entire Pi, resulting in loss of all data on Pi (but backed up on Github)
Issue | MyRIO appears to sporadically lose connection | 2017-01-16 | Medium | 25% | 0 | Possible issues identified
Issue | Servo shield for Raspberry Pi not functioning at all | 2017-01-18 | High | 100% | 1 | Servo shield was burnt out; new one purchased
Issue | Tri-Track motor appears to be malfunctioning | 2017-01-23 | Medium | 75% | 0 | Initial investigation shows this could be user error
Issue | Broken servo on the tri-track arm | 2017-03-01 | High | 100% | 1 | Servo has been replaced
Issue | Laser for laser navigation not powerful enough to be detected by the pi camera on the tri track | 2017-03-08 | High | 100% | 1 | Need to purchase a more powerful laser (PSTs have given solution to prove the laser navigating the tri track in gateway 3 and use a LED duirng VIVA day)
Issue | Pi camera cable too short | 2017-03-10 | Medium | 100% | 1 | Purchased a longer cable
Issue | STK software for Kinect not on the University machines | 2017-01-28 | High | 100% | 1 | Ray Cheung installed necessary firmware into all machines in W1.72
Issue | Delayed order for USB Microphone and Aux cable speaker | 2017-03-14 | Medium | 100% | 1 | Order received
Issue | Gimbal Motor order taking too long | 2017-03-25 | Medium | 100% | 1 | Reordered, and has been delivered
Issue | Microphones have not been received | 2017-03-25 | High | 100% | 1 | Microphones received
Issue | Broken servo on the tri-track arm | 2017-04-15 | High | 100% | 1 | Replacement servo received